## Vorgangstabelle1
MVD Task List
Description |  |  |  | Predecessor | Time needed | Manpower needed | Responsible | Comments
Pixel part
Module concept
Sensor
Single Chip Sensor
Desing
Production
Tests
Fullsize Prototype Sensors
Design
Production
Tests
Production
Production
Testing / Cataloging
Front-End ASIC
ToPix3
Design
|  |  | Production |  | 90 d
Tests
Fullsize Prototype
|  |  | Design |  | 180 - 240 d | 6-8 pm senior + 6-8 pm
|  |  | Production |  | 90 d
Tests
2nd iteration (optional)
Production
Production
Testing / Cataloging
Controller Chip
Concept
Design
Prototype
Production
Module Bus (Flex Hybrid)
Design
Test
Production
Hybridisation
FE Wafer thinning
Connection FE/Sensor
Connection Bus/Sensor
Connection Controller/Bus
Connection Cable/Bus
R&D on alternatives
Mounting
stave assembly
disk assembly
barrel mounting
disk mounting
Strip part
| Module concept |  |  |  | 200 d | 24 pm | Rosatom* | Rosatom = IHEP, Protvino + SINP MSU, Moscow +
Wedge Sensor
Design
Prototype
|  | Test |  |  | in total
|  | Production |  |  | 5 y: 2011-2015 | 360 pm | Rosatom | + IPTI, St Petersburg + RIMST, Zelenograd
Barrel Sensors
|  | Prototype (small size) |  |  | done
Full Size Prototypes
|  |  | Design |  | 60 d | 1
Commissioning
|  |  | Testing |  | 180 d | 2
|  | Final Senors | Commissioning
Production
|  |  | Q/A |  | 1a
Hybridisation
Module Design
|  | Lab Tests/Interconnection Studies |  |  | 90 d | 1
|  | Full Prototype Construction |  |  | 90 d | 3
|  | Testing |  |  | 60 d | 2
|  | Production (incl. Q/A) |  |  | 1a
Controller Chip
Design
FPGA Prototype
Tests
ASIC Design
Tests
Commisioning/Production
Slow Control
|  | Concept/Design |  |  | 1a | 2
Lab setup
Commisioning of Components/SC-Nodes
Module concept
Readout concept
Hybridisation
Mounting
stave assembly
disk assembly
barrel mounting
disk mounting
Close To Detector Electronics
Counting Room Electronics
Optical Data Transmission
Service Boards
Cables / Power
Powering Concept
Design
Small Scale Lab Setup(s)
Power Distribution Test Setup
Grounding/Shielding Test Setup
Full Supermodule (Stave) Setup
LV Power supplies
|  | Selection/Testing |  |  | 60 d
Commisioning
HV Power supplies
|  | Selection/Testing |  |  | 60 d
Commisioning
Power regulators
Design
Tests
Load/Thermal Tests
Irradiation Tests
Cables
|  | Selection/Spec Matching |  |  | 30 d
|  | Tests (Load/Mechanical/Rad Hardness/Connectivity) |  |  | 60 d | 2
Ordering
Mechanical Structures
Global Support
Design
Prototype
Test
Production
Local Pixel Barrel Support / Cooling
Design
Prototype
Test
Production
Local Pixel Disks Support / Cooling
Design
Prototype
Test
Production
Local Strip Barrel Support / Cooling
Design
Prototype
Test
Production
Local Strip Disks Support / Cooling
|  | Design |  |  | 120 d: 2011 | 6 pm | Rosatom
|  | Prototype |  |  | 120 d: 2012 | 12 pm | Rosatom
|  | Test |  |  | 30 d: 2012 | 3 pm | Rosatom
|  | Production |  |  | 150 d: 2013-2014 | 12 pm | Rosatom
Cooling
Pixel Pipes
Pixel Manifolds
Strip Pipes
Strip Manifolds
Cooling plant
DCS
Mounting
MVD mounting
MVD installation
Commissioning
Milestones

## Tabelle1
Sensors
| Prototype (small size) |  | done
Full Size Prototypes
|  | Design | 60 d | 1
Commissioning
|  | Testing | 180 d | 2
| Final Senors | Commissioning
Production
|  | Q/A | 1a
Hybridisation
Module Design
| Lab Tests/Interconnection Studies |  | 90 d | 1
| Full Prototype Construction |  | 90 d | 3
| Testing |  | 60 d | 2
| Production (incl. Q/A) |  | 1a
Controller Chip
Design
FPGA Prototype
Tests
ASIC Design
Tests
Commisioning/Production
Slow Control
| Concept/Design |  | 1a | 2
Lab setup
Commisioning of Components/SC-Nodes
Construction
Powering Concept
Design
Small Scale Lab Setup(s)
Power Distribution Test Setup
Grounding/Shielding Test Setup
Full Supermodule (Stave) Setup
Power supplies
| Selection/Testing |  | 60 d
Commisioning
Power regulators
Design
Tests
Load/Thermal Tests
Irradiation Tests
Patch panels
Cables
| Selection/Spec Matching |  | 30 d
| Tests (Load/Mechanical/Rad Hardness/Connectivity) |  | 60 d | 2
Ordering