## Slide 1
MVD Assembly
  Two half frame done – Dimension Tested
  Ancillaries for Frames done – Dimension Tested
  Frame Assembly & Final Machining – must be done
  Special & Precision Screws - must be done
  Fixing Point of the Sub-Structures – Defined
  Fixing Point for Strip Disk must be defined
  MVD Assembly Sequence – Defined
  Open Items: Services Routing, Patch Panels

## Slide 2
MVD Integration
  MVD Aligned & Fixed on Central Frame
  Ref. Bosses: two options  gluing/machining
  Open Item: Central Frame Definition
  Critical Point: Cross Pipe Position/Geometry
  MVD Final Survey
  Position of target point must be defined
  MVD Services Routing
  Tests must be defined
  Patch Panel Position must be defined
  Open Item: Services Routing Outside the Magnet

## Slide 3
MVD Pixel-Mechanics
Barrel & Disks Geometry Defined
Barrel & Disks Assembly Procedure Defined but NOT TESTED
Barrel & Disks Cooling Tubes Assembly Defined & Tested Assembly Tooling to be defined

## Slide 4
Services Routing - Patch Panels Very preliminary
PATCH PANELS OUTSIDE STT/TPC VOLUME – PIXEL DISKS
PATCH PANELS INSIDE STT/TPC VOLUME – BARREL (PIXEL+STRIP)
CRITICITY!!!
DIFFERENT PATH
FOR CABLES AND TUBES

## Slide 5
Services Routing - Patch Panels Very preliminary

## Slide 6
Services Routing - Patch Panels Very preliminary

## Slide 7
Services Routing - Patch Panels Very preliminary

## Slide 8
CENTRAL FRAME DESIGN – TARGET: RIGIDITY  TARGET: MAX DEFORMATION < 50μm
1ST STEP – CURRENT DESIGN  142 μm MVD SUPPORT AREA
STATIC LOAD (CROSS PIPE+MVD+STT)
M55J/ROHACELL/M55J+TITANIUM (CONNECTING PART )
CENTRAL FRAME DEFINITION

## Slide 9
CENTRAL FRAME DESIGN – TARGET RIGIDITY  TARGET DEFORMATION < 50μm
2nd STEP – CENTRAL WINDOWS REMOVED 124 μm MVD SUPPORT AREA
STATIC LOAD (CROSS PIPE+MVD+STT)
M55J/ROHACELL/M55J+TITANIUM (CONNECTING PART )

## Slide 10
CENTRAL FRAME DESIGN – TARGET RIGIDITY  TARGET DEFORMATION < 50μm
3rd STEP – ALL WINDOWS REMOVED 104 μm MVD SUPPORT AREA
STATIC LOAD (CROSS PIPE+MVD+STT)
M55J/ROHACELL/M55J+TITANIUM (CONNECTING PART )

## Slide 11
NEXT STEPS: RIBS EMBEDDED INTO THE STRUCTURE
STRESS INDUCED TO THE CROSS-PIPE
CONNECTING PARTS MADE BY EPM203 (EPOXY/GLASS)
OR CYANATE/CARBON FIBRE
CENTRAL FRAME DEFINITION

## Slide 12
Mechanics TDR
DONE & WRITTEN
Frame:
  Geometry, description.
  Structural constraint.
  Feasibility.
Barrel:
  Geometry (sensors distribution)
  Physical constraint.
  Support and frame connection.
Disks:
  Geometry (sensors distribution)
  Physical constraint.
  Frame connection.
        TO BE DONE
        Assembly sequence.
        Assembly tools.
        End stave electronics boards support definition.
        Mechanical integration with strip parts (barrel & disks)

## Slide 13
MVD Pixel-cooling
carbon foam tested
disks cooling Defined & tested, small disks to be optimized
barrel cooling Defined &tested, to be optimized
Open Item: test with master bond glue
cfd simulation
cooling plant-first drafs of pixel parts

## Slide 14
Cooling TDR
DONE & WRITTEN
Pixel cooling system:
  Pixel power
  Thermal request
  Working condition
Test on carbon foam (Young modulus and thermal conductivity at different radiation fields)
Disks cooling system:
  Description
  Fem analyses and test results on prototype
  Pressure drop
Barrel cooling system:
  Description
  Fem analyses and test results on prototype
CFD simulation
Cooling plant:
  Description
  Pixel modularity
  First drafts
        TO BE DONE
        Tests with Master Bond glue
        Cooling for the End stave electronics boards
        Strip part integration in the cooling plant
        Final design of the cooling plant