## Sheet1
	2016					2017
	6	7	8	9	10	11	12	1	2	3	4	5	6
crystal tests
APDs (2000 pcs)
irradiation	400/week
2nd screening	150/week
matching
reflective foil production
capsule production
detector assembly		40/week
ASIC PCBs (710 pcs)
PCB production	1 month + order + vacation time
mounting/bonding			8 weeks
testing				90/week
module assembly
Backplane PCB (180 pcs)
design
testing	testing of prototypes + rad hardness of components
production
testing					20/week
signal cables (890 pcs)
ordering
tayloring
mounting on connector PCBs				38/week
slice assembly
module placement
BPL mounting
cable routing
SC & DAQ
cooling
installation of Bo cooling
test with slice