## Vorgangstabelle1
MVD Task List
Description |  |  |  | Predecessor | Time needed | Manpower needed | Responsible | Comments
Pixel part
Module concept
Sensor
Single Chip Sensor
Desing
Tests
Fullsize Sensors
Design
Production
Tests
Production
Front-End ASIC
ToPix3
Design
|  |  | Production |  | 90 d
Tests
Fullsize Prototype
Design
Production
Tests
Production
Controller Chip
Concept
Design
Prototype
Production
Flex Hybrid
Design
Test
Production
Hybridisation
Bump Bonding R&D
Thinning R&D
Alternative Technologies
Production
Bump Bonding
Gluing
Wire/Tab Bonding
Strip part
Module concept
Readout concept
Hybridisation
Construction
Off-detector Electronics
Data transmission
Data receiver at control room
Production
Cables / Power
Cable plan
Grounding scheme
Schielding scheme
Power supplies
Power regulators
Patch panels
Mechanical Structures
Global Support
Design
Prototype
Test
Production
Local Pixel Barrel Support / Cooling
Design
Prototype
Test
Production
Local Pixel Disks Support / Cooling
Design
Prototype
Test
Production
Local Strip Barrel Support / Cooling
Design
Prototype
Test
Production
Local Strip Disks Support / Cooling
Design
Prototype
Test
Production
Cooling
Cooling pipe plan
Pipes
Manifolds
Cooling device
Mounting
Commissioning
Milestones