## sheet
MVD Task List
Description |  |  |  | Predecessor | Time needed | Manpower needed | Responsible | Comments
Pixel part | [6 empty] | Torino/Jülich
| Module concept | [5 empty] | Torino/Jülich | decision on EPI pending
| Sensor | [5 empty] | Torino
Single Chip Sensor
Design
Production
Tests
Fullsize Prototype Sensors
Design
Production
Tests
Production
Production
Testing / Cataloging
| Front-End ASIC | [5 empty] | Torino
ToPix3
|  |  | Design |  | 200d
|  |  | Production |  | 90 d
|  |  | Tests |  | 200d
|  |  | Radiation test |  | 100d
Fullsize Prototype
|  |  | Design |  | 180 - 240 d | 6-8 pm senior + 6-8 pm
|  |  | Production |  | 90 d
Tests
2nd iteration (optional)
Production
Production
Testing / Cataloging
| Controller Chip | [5 empty] | Torino
Concept
Design
Prototype
Production
| Module Bus (Flex Hybrid) | [5 empty] | Torino/Jülich
Design
Test
Production
| Hybridisation | [5 empty] | Torino
FE Wafer thinning
Connection FE/Sensor
Connection Bus/Sensor
Connection Controller/Bus
Connection Cable/Bus
R&D on alternatives
| Mounting | [5 empty] | Torino/Jülich
stave assembly
disk assembly
barrel mounting
disk mounting
Strip part
| Module concept |  |  |  | 200 d | 24 pm | Rosatom* | Rosatom = IHEP, Protvino + SINP MSU, Moscow +
Wedge Sensor
Design
Prototype
|  | Test |  |  | in total
|  | Production |  |  | 5 y: 2011-2015 | 360 pm | Rosatom | + IPTI, St Petersburg + RIMST, Zelenograd
| Barrel Sensors | [5 empty] | Bonn
|  | Prototype (small size) |  |  | done
Full Size Prototypes
|  |  | Design |  | 60 d | 1
Commissioning
|  |  | Testing |  | 180 d | 2
|  | Final Senors | Commissioning
Production
|  |  | Q/A |  | 1a
| Hybridisation | [5 empty] | Bonn/Jülich
Module Design
|  | Lab Tests/Interconnection Studies |  |  | 90 d | 1
|  | Full Prototype Construction |  |  | 90 d | 3
|  | Testing |  |  | 60 d | 2
|  | Production (incl. Q/A) |  |  | 1a
| Front-End | [5 empty] | Bonn/Jülich
| Controller Chip | [5 empty] | Bonn
Design
FPGA Prototype
Tests
ASIC Design
Tests
Commisioning/Production
| Slow Control | [5 empty] | Bonn/Jülich
|  | Concept/Design |  |  | 1a | 2
Lab setup
Commisioning of Components/SC-Nodes
| Mounting | [5 empty] | Bonn/Jülich/Rosatom
stave assembly
disk assembly
barrel mounting
disk mounting
Close To Detector Electronics | [6 empty] | Torino/Jülich | optical data transmission etc, see above at least partly
Service Boards
Counting Room Electronics | [6 empty] | Jülich (ZEL)
| Board Development |  |  |  | 1,5 a | 1.5
| FPGA Code Development |  |  |  | 2a | 1
| Setup of Testsystem |  |  |  | 0,5 a | 1
| Integration with Compute-Node |  |  |  | 1 year | 2
Optical Data Transmission | [6 empty] | Torino/Jülich
Cables / Power | [6 empty] | all
Powering Concept
Design
Small Scale Lab Setup(s)
Power Distribution Test Setup
Grounding/Shielding Test Setup
Full Supermodule (Stave) Setup
LV Power supplies
|  | Selection/Testing |  |  | 100d
Commisioning
HV Power supplies
|  | Selection/Testing |  |  | 100d
Commisioning
Power regulators
Design
Tests
Load/Thermal Tests
Irradiation Tests
Cables
|  | Selection/Spec Matching |  |  | 30 d
|  | Tests (Load/Mechanical/Rad Hardness/Connectivity) |  |  | 100d | 2
Ordering
Mechanical Structures | [6 empty] | all
| Global Support | [5 empty] | Torino
Design
Tool development
Prototype
Test
Production
| Local Pixel Barrel Support / Cooling | [5 empty] | Torino
Design
Tool development
Prototype
Test
Production
| Local Pixel Disks Support / Cooling | [5 empty] | Torino
Design
Tool development
Prototype
Test
Production
| Local Strip Barrel Support / Cooling | [5 empty] | Jülich/Bonn
|  | Design |  |  | 30 d
|  | Tool development |  |  | 180 d
|  | Prototype |  |  | 15 d
|  | Test |  |  | 30 d
|  | Production |  |  | 180 d
Local Strip Disks Support / Cooling
|  | Design |  |  | 120 d: 2011 | 6 pm | Rosatom
|  | Prototype |  |  | 120 d: 2012 | 12 pm | Rosatom
|  | Test |  |  | 30 d: 2012 | 3 pm | Rosatom
|  | Production |  |  | 150 d: 2013-2014 | 12 pm | Rosatom
Addt'nal Disks | [6 empty] | Rosatom
Cooling | [6 empty] | all
Pixel Pipes
Pixel Manifolds
Strip Pipes
Strip Manifolds
Cooling plant
DCS | [6 empty] | Jülich (ZEL) | interface to DCS group / Dan P.
Mounting | [6 empty] | all
MVD mounting
MVD installation
Commissioning | [6 empty] | all
Milestones | [7 empty] | TDR 2010/2011